## Sheet1
PBI # s |  | To-Do | In progress | Completed
PBI 1 | As an election official I want the system to run OPL and IR elections fairly and give audit logs so that we can run elections Acceptance Criteria: The system alway runs correctly for OPL and IRV. Definition of Done: pass all unit tests, system test, regression test and documentation done Effort: Medium PBI Author(s): Luke Chen |  |  | PBI 5 Code OPL(Rohan)
PB1 5 | As an election official I want to be able to bring in multiple files instead of a single file so that we can bring in different files from different balloting locations and run an election. Note: We are interested in functionality and not the individual tasks for the PBI. Do not create tasks at this time. Acceptance Criteria: The votecountsystem can take in multiple files and count the votes across those files and can give us the results of the election. This feature can be done on any election type. Definition of Done: pass all unit tests, system test, regression test and documentation done Effort: Medium PBI Author(s): Isaac Xiong |  |  | PBI 5 Code IRV(Rohan)
PBI 13 | As an election official, I want to only count IRV ballots that have at least half of the candidates ranked so that we only count the ones that give more options. Acceptance Criteria: Invalidated ballots must be removed from the election when the software is run. Ballots have the number of candidates voted for divided by the total number of candidates rounded up from .5 or above to the next higher integer value and must be at least half for each ballot to be valid. Definition of Done: System and unit tests show that the correct ballots are discarded Effort: Medium PBI Author(s): Abdikarim Fareh |  |  | PBI 5 Documentation (Rohan)
PBI 3 | As an election official I want ballots for PO to be brought in from files so that I can run an election that is determined by PO voting Acceptance Criteria: Files with PO voting system can be run Definition of Done: pass all unit tests, system test, regression test and documentation done Effort: Medium PBI Author: Rohan Abraham |  |  | PBI 5 Code main(Rohan)
PBI 3 Code (Isaac)
PBI 1 OP Break Tie - between Parties
PBI 1 OP Break Tie - between candidates
|  |  | PBI 1 OP and IR improve testing | PBI 5 Testing(Rohan)
|  |  | PBI 1 OP and IR improve documentation | PBI 5 Code PO(Rohan)
PBI 13 filter IRV ballots with less than 50% (Luke)
PBI 13 Testing
PBI 13 Documentation
PBI 3 add PO to main driver
PBI 3 add PO class
PBI 3 Documentation